## Actual Plan
Project Management Internship Program
Duration: 12 Weeks
Week | Day | Activity | Status | Person Responsible
Week 1: Orientation & Introduction to Project Management |  |  | N/A
1 | Day 1 | Welcome Session & Team Introductions (led by Fahad)
| Day 2 | Welcome Session & Team Introductions (led by Fahad) |  | Both
| Day 3 | Introduction to Project Management & Requirement Gathering Fundamentals | Wed | Rinah
| Day 4 | Understanding ERDs (Entity Relationship Diagrams) and Flowcharts | thur | Rinah
| Day 5 | Understanding ERDs (Entity Relationship Diagrams) and Flowcharts + Assignment | Friday | Sharifah
Week 2: Understanding User Stories |  |  | N/A
2 | Day 1 | Review ERD/Flowchart Assignment |  | Both
| Day 2 | Writing User Stories – Walkthrough & Example 1 |  | Rinah
| Day 3 | Writing User Stories – Example 2 |  | Rinah
| Day 4 | User Stories Assignment
| Day 5 | Review Assignment & Leave Another Challenge |  | Both
Week 3: Deep Dive into User Stories & Diagrams |  |  | N/A
3 | Day 1 | Review Previous Assignment |  | Both
| Day 2 | User Stories – Example 3 & New Assignment |  | Rinah
| Day 3-4 | Combine ERDs, Flowcharts, and User Stories in a Single Case Study Assignment
| Day 5 | Review Work & Discussion |  | Both
Week 4: UI/UX Design Introduction |  |  | N/A
4 | Day 1 | Introduction to UI/UX Tools (Installing Figma, Photoshop, etc.) |  | Rinah
| Day 2 | Sketching Interfaces – Lo-fi & Hi-fi Wireframes + Assignment |  | Rinah
| Day 3 | Assignment Work Day (Wireframes)
| Day 4 | Review Wireframes |  | Both
| Day 5 | Introduction to Photoshop & Adobe Illustrator |  | Jane
Week 5: More UI/UX Design |  |  | N/A
5 | Day 1 | Photoshop & Illustrator Practice & leave assignment |  | Jane
| Day 2 | Review assignment |  | Jane
| Day 3 | Introduction to Figma – Design Principles + Assignment |  | Rinah
| Day 4 | Assignment Work Day (Wireframes)
| Day 5 | Review Designs |  | Both
Week 6: React Fundamentals |  |  | N/A | Arop
6 | Day 1 | Intro & Environment Setup
| Day 2 | JSX & Components
| Day 3 | State & Events
| Day 4 | Lists & Conditional Rendering
| Day 5 | Mini Project
Weeks 7: Hooks, Routing & Forms |  |  | N/A | Arop
7 | Day 1 | Review of the Mini Project
| Day 2 | Use effect & UseRef
| Day 3 | Routing
| Day 4 | Forms & Input Handling
| Day 5 | API Integration , Leave Mini Project
Weeks 8: Advanced React & State Management |  |  | N/A | Arop
8 | Day 1 | Context API
| Day 2 | Custom Hooks
| Day 3 | Redux Toolkit (or Zustard)
| Day 4 | Component Patterns & Optimization
| Day 5 | Mini Project
Weeks 9: QA & Testing & Final Project Overview |  |  | N/A | Rinah
9 | Day 1-4 | Creating Test cases and Testing Overview
| Day 5 | Final Project Walkthrough
Weeks 10-12: FINAL PROJECT IMPLEMENTATION |  |  | N/A | Both
10 |  | Final Project Implementation
11
12